## Cover
Lean Six Sigma Project Definition
Project Number (from your project tracking tool) :
Project Title (50 words or less) :
Local Champion Name :
Assignment Priority : | High Medium Low
Assignment :
Black or Green Belt Name :
Finance Rep Name :
© Lean Methods Group. Except as may be expressly authorized by a written license agreement signed by Lean Methods Group, no portion may be altered, rewritten, edited, modified or used to create any derivative works.

## Blank PDW
Project Definition Worksheet
Project Title:
| Step | Element | Answer/Tool
Define and Scope Problem | Identify the Business Gap | What is the specific problem (project idea) affecting the success of your business?
Name the business metric associated with this problem (existing management performance indicator)?
Who are the internal and/or external customers most affected by this problem?
Is there competitive pressure creating a need to close this gap?
Is there a business strategy driving the need for a change?
Where is the problem occurring (geographic or process location)?
When was the problem first observed (specify month/year)?
How Much? What is the extent or magnitude of the problem as measured by your business metric?
How do you know this is a problem?
|  | Summarize items above into a Preliminary Business Case | Project Charter
| Document the Process | What is the output product or service delivered to the customer related to the business problem?
Name the business process delivering the product or service. Think in terms of a process that can be mapped.
|  | Develop a High Level "As-Is" Process Map of the above business process. (Illustrate spatial/geographic flow if relevant to business gap.) This typically includes 5 to 7 major steps of a process. | SIPOC, High Level Value Stream Map or Spaghetti Diagram
Are there more than two business departments/functions/locations involved? If yes, the problem is likely too broad and a scoping session using scoping tools should be executed.
| Collect & Translate the VOC | What are the customer requirements? (Verbal and/or Numerical)
What are their specifications for each requirement?
What are the performance gaps in satisfying the customer requirements?
Is there a performance gap vs. your competition that needs to be closed? Which competitors? Which requirements?
Which customer requirement(s) will be the focus of this improvement project? If more than 2 requirements are identified, the scope of the project may be too broad.
Determine Project Objectives and Benefits | Define Metrics & Defects | What is/are the defect(s)?
Name the Primary Metric that measures the defect rate? (The Primary Metric) will be the yardstick for tracking success of the project.
Name any Secondary Metric(s) that should improve as a result of completing the project.
Name the Consequential Metrics which measure potential negative consequences of successfully improving the Primary Metric.
Identify which sources of data (reports, collection sheets, inspection points, etc.) are available to measure the metrics above.
Is there sufficient historical data for all of the project metrics? If no data exists, then how do we know that there is a gap that needs to be closed?
How do the project metrics align with the business metrics?
| Establish Preliminary Baseline & Entitlement | Create data collection plan if insufficient project metric data exists. | Data Collection Plan
Estimate the Baseline performance level of this Primary Metric.
Estimate the Entitlement (best short term observed historical performance) and/or Benchmark of this Primary Metric.
| Develop Problem & Objective Statements | Write the Problem Statement in sentence format using the format: <What><Where><When><How Much><How do you know>.
Write a S.M.A.R.T. Objective Statement as follows: "Improve {primary metric} from {baseline level} to {target level (70% toward entitlement)} by {timeframe MM/YYYY}.
| Estimate Financial Benefit | Who is the Finance Representative assigned to value the financial impact of this Six Sigma project?
What is the cost of a defect/cost of poor quality?
List the Financial Metric(s) that will be used to track the improvement of the primary metric in the local currency.
Complete the Original Forecast with the Financial Representative.
|  | Complete Cost Benefit Analysis with the Finance Representative. | Cost Benefit Analysis
Create Project Charter | Confirm Improvement Methodology | What is the most likely improvement path that will be followed? (e.g. Six Sigma, SCORE Event, DMAIC, Combined Approach)
| Define Project Roles & Responsibilities | Who will lead the project and what is their role (BB, GB, Lean Facilitator…)?
Who is the Champion of this project?
Identify the Process Owner.(person with primary responsibility for ongoing operation of impacted process)
Identify the project team members (typically 3-6 people who have a broad level of expertise or process knowledge).
Who will be affected by making a change to the process?
Who are the project stakeholders?
|  | Complete Stakeholder Analysis and recommend action plan, if appropriate. | Stakeholder Analysis
| Identify Project Risks | Does this project compete with other projects for resources and priority?
Will lack of data delay or inhibit project execution?
Is significant capital or IT expenditure expected?
Describe any risks associated with Stakeholder support?
Describe any customer-related risks that could impact the project?
Describe any competition-related risks that could impact the project?
Is there a similar project in progress?
Have their been previous efforts to close this business gap? What were the results?
| Establish Project Timeline | When is the project estimated to start?
When is the project estimated to be completed?
What are intermediate milestones? (e.g. Completing each of the DMAIC phases)
Have the risks identified above been incorporated into the estimation of the project timeline?
| Create Comm. Plan | Who needs to be made aware of this project?
|  | Complete Communication Plan | Communication Plan

## Call Center Example
Project Definition Worksheet
| Project Title: | Improve First Call Resolution Rate for Health Insurance Inquiries
| Step | Element | Answer/Tool
Define and Scope Problem | Identify the Business Gap | What is the specific problem (project idea) affecting the success of your business? | Customers often have to make several calls to our customer line to have their issue resolved.
|  | Name the business metric associated with this problem (existing management performance indicator)? | First Call Resolution Rate (FCRR - Call resolved on 1st attempt/Total calls on a daily basis)
|  | Who are the internal and/or external customers most affected by this problem? | Customer Service Agents, Call center supervisor, client
|  | Is there competitive pressure creating a need to close this gap? | Yes - last year 10% of our current clients switched to a competitor
|  | Is there a business strategy driving the need for a change? | Yes - tied to goals of Customer Satisfaction, Accessibility, Customer Retention
|  | Where is the problem occurring (geographic or process location)? | All US Call Centers
|  | When was the problem first observed (specify month/year)? | Since we started collecting data on FCRR in 2004
|  | How Much? What is the extent or magnitude of the problem as measured by your business metric? | Historically, only 80% of all calls are resolved on the first attempt
|  | How do you know this is a problem? | Weekly FCRR Reports
|  | Summarize items above into a Preliminary Business Case | Project Charter
| Document the Process | What is the output product or service delivered to the customer related to the business problem? | Information, Authorizations, Medical Advice
|  | Name the business process delivering the product or service. Think in terms of a process that can be mapped. | Customer service - Issue Resolution
|  | Develop a High Level "As-Is" Process Map of the above business process. (Illustrate spatial/geographic flow if relevant to business gap.) This typically includes 5 to 7 major steps of a process. | SIPOC, High Level Value Stream Map or Spaghetti Diagram
|  | Are there more than two business departments/functions/locations involved? If yes, the problem is likely too broad and a scoping session using scoping tools should be executed. | YES - may need to narrow to a specific call center or type of inquiry
| Collect & Translate the VOC | What are the customer requirements? (Verbal and/or Numerical) | No need to call back, Resolved quickly, Resolved correctly
|  | What are their specifications for each requirement? | 1 call, depends on issues, y/n
|  | What are the performance gaps in satisfying the customer requirements? | 20% calls not resolved the first time
|  | Is there a performance gap vs. your competition that needs to be closed? Which competitors? Which requirements? | Based on an industry benchmark study Happy Health Care has a 95% FCRR. We were rated 8th in FCRR in the study.
|  | Which customer requirement(s) will be the focus of this improvement project? If more than 2 requirements are identified, the scope of the project may be too broad. | FCRR for Dental Claims in Texas
Determine Project Objectives and Benefits | Define Metrics & Defects | What is/are the defect(s)? | Any call abandoned, re-routed to another agent, requiring a follow-up or answered by voice mail during business hours
|  | Name the Primary Metric that measures the defect rate? (The Primary Metric) will be the yardstick for tracking success of the project. | Dental Claims Issues FCRR
|  | Name any Secondary Metric(s) that should improve as a result of completing the project. | Overall FCRR, Call Volume
|  | Name the Consequential Metrics which measure potential negative consequences of successfully improving the Primary Metric. | Accuracy of response, Average Handle Time
|  | Identify which sources of data (reports, collection sheets, inspection points, etc.) are available to measure the metrics above. | Weekly FCRR Reports, Audits for Accuracy, Weekly Call Volume Reports
|  | Is there sufficient historical data for all of the project metrics? If no data exists, then how do we know that there is a gap that needs to be closed? | yes, >1 yr of data exists
|  | How do the project metrics align with the business metrics? | Improving FCRR tied to customer satisfaction & retention
| Establish Preliminary Baseline & Entitlement | Create data collection plan if insufficient project metric data exists. | Data Collection Plan
|  | Estimate the Baseline performance level of this Primary Metric. | Dental Claims Issues FCRR approx. 70%
|  | Estimate the Entitlement (best short term observed historical performance) and/or Benchmark of this Primary Metric. | Medical Claim Issues FCRR approx. 90%
| Develop Problem & Objective Statements | Write the Problem Statement in sentence format using the format: <What><Where><When><How Much><How do you know>. | For the last 12 months Dental Claim FCRR was 70% in Texas based on the weekly FCRR report.
|  | Write a S.M.A.R.T. Objective Statement as follows: "Improve {primary metric} from {baseline level} to {target level (70% toward entitlement)} by {timeframe MM/YYYY}. | Increase the Dental Claim FCRR from 70% to 84% by 11/12/06 as measured by the weekly FCRR report
| Estimate Financial Benefit | Who is the Finance Representative assigned to value the financial impact of this Six Sigma project? | S. Dixon
|  | What is the cost of a defect/cost of poor quality? | $1/call not resolved
|  | List the Financial Metric(s) that will be used to track the improvement of the primary metric in the local currency. | FTE (Full Time Equivalent)
|  | Complete the Original Forecast with the Financial Representative. | 4 FTEs ($200,000/yr)
|  | Complete Cost Benefit Analysis with the Finance Representative. | Cost Benefit Analysis
Create Project Charter | Confirm Improvement Methodology | What is the most likely improvement path that will be followed? (e.g. Six Sigma, SCORE Event, DMAIC, Combined Approach) | Integrated LSS Approach
| Define Project Roles & Responsibilities | Who will lead the project and what is their role (BB, GB, Lean Facilitator…)? | B. Thornton (BB)
|  | Who is the Champion of this project? | T. Wong
|  | Identify the Process Owner.(person with primary responsibility for ongoing operation of impacted process) | A. Yamoto
|  | Identify the project team members (typically 3-6 people who have a broad level of expertise or process knowledge). | W. Houston, P. Smith, G. Hines, L. David
|  | Who will be affected by making a change to the process? | CSRs (Customer Service Representatives), Client
|  | Who are the project stakeholders? | T. Wong, A. Yamoto, K. Kline, J. Wu
|  | Complete Stakeholder Analysis and recommend action plan, if appropriate. | Stakeholder Analysis
| Identify Project Risks | Does this project compete with other projects for resources and priority? | Yes - if IT Solution is required, project will compete with other projects for resources
|  | Will lack of data delay or inhibit project execution? | Not expected
|  | Is significant capital or IT expenditure expected? | Unknown
|  | Describe any risks associated with Stakeholder support? | None detected
|  | Describe any customer-related risks that could impact the project? | None expected
|  | Describe any competition-related risks that could impact the project? | nothing specific
|  | Is there a similar project in progress? | Yes - similar project for Medical Benefits in NW Region
|  | Have their been previous efforts to close this business gap? What were the results? | Yes - Suggestion Box recommendations were implemented with little impact
| Establish Project Timeline | When is the project estimated to start? | 2016-06-12
|  | When is the project estimated to be completed? | 2016-11-12
|  | What are intermediate milestones? (e.g. Completing each of the DMAIC phases) | Define - 7/12/16 Measure - 8/12/16 Analyze - 9/12/16 Improve - 10/12/16 Control - 11/12/16
|  | Have the risks identified above been incorporated into the estimation of the project timeline? | yes
| Create Comm. Plan | Who needs to be made aware of this project? | CSRs, CSR Supervisors, Executive Management Team
|  | Complete Communication Plan | Communication Plan

## Cookie Example
Project Definition Worksheet
| Project Title: | Reduced Scrapped Cookies
| Step | Element | Answer/Tool
Define and Scope Problem | Identify the Business Gap | What is the specific problem (project idea) affecting the success of your business? | For every batch of cookies baked a significant amount of them are scrapped
|  | Name the business metric associated with this problem (existing management performance indicator)? | Daily Scrap Rate (#Cookies Scrapped/Total Cookies Baked), Returns
|  | Who are the internal and/or external customers most affected by this problem? | Regional General Manager, Grocery Store, Consumer
|  | Is there competitive pressure creating a need to close this gap? | OERO Cookies continues to reduce it's price
|  | Is there a business strategy driving the need for a change? | Aligned with strategy of increasing profit margins by 10% this year
|  | Where is the problem occurring (geographic or process location)? | NW US Bakeries
|  | When was the problem first observed (specify month/year)? | Always a problem, increased after new ovens installed
|  | How Much? What is the extent or magnitude of the problem as measured by your business metric? | approximately 25% scrap rate
|  | How do you know this is a problem? | Weekly scrap report, scrap bins
|  | Summarize items above into a Preliminary Business Case | Project Charter
| Document the Process | What is the output product or service delivered to the customer related to the business problem? | Cookie
|  | Name the business process delivering the product or service. Think in terms of a process that can be mapped. | Mixing & Baking
|  | Develop a High Level "As-Is" Process Map of the above business process. (Illustrate spatial/geographic flow if relevant to business gap.) This typically includes 5 to 7 major steps of a process. | SIPOC, High Level Value Stream Map or Spaghetti Diagram
|  | Are there more than two business departments/functions/locations involved? If yes, the problem is likely too broad and a scoping session using scoping tools should be executed. | YES - may need to narrow to a specific bakery in the NW region
| Collect & Translate the VOC | What are the customer requirements? (Verbal and/or Numerical) | good tasting, chewy, fresh, look good, not cracked, consistent shape
|  | What are their specifications for each requirement? | not all defined - visual inspection and taste testing criteria used
|  | What are the performance gaps in satisfying the customer requirements? | Excessive scrap due to cracked chocolate chip cookies
|  | Is there a performance gap vs. your competition that needs to be closed? Which competitors? Which requirements? | OERO Cookies have fewer cracked cookies/packed based on past benchmarking study
|  | Which customer requirement(s) will be the focus of this improvement project? If more than 2 requirements are identified, the scope of the project may be too broad. | Scrap due to cracked chocolate chip cookies
Determine Project Objectives and Benefits | Define Metrics & Defects | What is/are the defect(s)? | Any cookie that is cracked
|  | Name the Primary Metric that measures the defect rate? (The Primary Metric) will be the yardstick for tracking success of the project. | Scrap Rate for Cracked Cookies
|  | Name any Secondary Metric(s) that should improve as a result of completing the project. | Returns due to cracked cookies
|  | Name the Consequential Metrics which measure potential negative consequences of successfully improving the Primary Metric. | taste, chewiness
|  | Identify which sources of data (reports, collection sheets, inspection points, etc.) are available to measure the metrics above. | daily scrap reports
|  | Is there sufficient historical data for all of the project metrics? If no data exists, then how do we know that there is a gap that needs to be closed? | yes, >1 yr of data exists
|  | How do the project metrics align with the business metrics? | Scrap due to cracks is a component of total scrap. Total Scrap reduces profit margin
| Establish Preliminary Baseline & Entitlement | Create data collection plan if insufficient project metric data exists. | Data Collection Plan
|  | Estimate the Baseline performance level of this Primary Metric. | Cracked Chocolate Chip Scrap Rate approx. 15%
|  | Estimate the Entitlement (best short term observed historical performance) and/or Benchmark of this Primary Metric. | 5% scrap rate demonstrated last December
| Develop Problem & Objective Statements | Write the Problem Statement in sentence format using the format: <What><Where><When><How Much><How do you know>. | The scrap rate due to cracked chocolate chip cookies in the NW bakeries is 15% for the past 12 months based on daily scrap reports
|  | Write a S.M.A.R.T. Objective Statement as follows: "Improve {primary metric} from {baseline level} to {target level (70% toward entitlement)} by {timeframe MM/YYYY}. | Reduce the scrap rate due to cracks from 15% to 8% by 11/12/06 as measured by the daily scrap report
| Estimate Financial Benefit | Who is the Finance Representative assigned to value the financial impact of this Six Sigma project? | S. Dixon
|  | What is the cost of a defect/cost of poor quality? | $0.08/scrapped cookie
|  | List the Financial Metric(s) that will be used to track the improvement of the primary metric in the local currency. | Scrap $
|  | Complete the Original Forecast with the Financial Representative. | $204,400/yr savings based on current production rates
|  | Complete Cost Benefit Analysis with the Finance Representative. | Cost Benefit Analysis
Create Project Charter | Confirm Improvement Methodology | What is the most likely improvement path that will be followed? (e.g. Six Sigma, SCORE Event, DMAIC, Combined Approach) | DMAIC
| Define Project Roles & Responsibilities | Who will lead the project and what is their role (BB, GB, Lean Facilitator…)? | B. Thornton (BB)
|  | Who is the Champion of this project? | T. Wong
|  | Identify the Process Owner.(person with primary responsibility for ongoing operation of impacted process) | A. Yamoto
|  | Identify the project team members (typically 3-6 people who have a broad level of expertise or process knowledge). | W. Houston, P. Smith, G. Hines, L. David
|  | Who will be affected by making a change to the process? | Production Team & Supervisors
|  | Who are the project stakeholders? | T. Wong, A. Yamoto, K. Kline, J. Wu
|  | Complete Stakeholder Analysis and recommend action plan, if appropriate. | Stakeholder Analysis
| Identify Project Risks | Does this project compete with other projects for resources and priority? | Yes - if capital is required, project will compete with other projects for funding
|  | Will lack of data delay or inhibit project execution? | Not expected
|  | Is significant capital or IT expenditure expected? | Unknown
|  | Describe any risks associated with Stakeholder support? | None detected
|  | Describe any customer-related risks that could impact the project? | Cannot save on scrap while compromising on taste and chewiness
|  | Describe any competition-related risks that could impact the project? | nothing specific
|  | Is there a similar project in progress? | NO
|  | Have their been previous efforts to close this business gap? What were the results? | Yes - scrap reduced last year from 30% to 20% but has risen back to 25%
| Establish Project Timeline | When is the project estimated to start? | 2016-06-12
|  | When is the project estimated to be completed? | 2016-11-12
|  | What are intermediate milestones? (e.g. Completing each of the DMAIC phases) | Define - 7/12/16 Measure - 8/12/16 Analyze - 9/12/16 Improve - 10/12/16 Control - 11/12/16
|  | Have the risks identified above been incorporated into the estimation of the project timeline? | yes
| Create Comm. Plan | Who needs to be made aware of this project? | Production Supervisors, QC manager
|  | Complete Communication Plan | Communication Plan